# The Plan

Written 11 August 2026, after 48 dead candidates. For execution on resume.

## 0. What "failure is not an option" can honestly mean

It cannot mean *guaranteed success*. The base rates are known and they are brutal: of 937

Stripe-verified indie founders, 54% earn nothing and roughly 5% exceed US$8.333/month. Anyone

who promises around that is selling something.

It can mean something harder and more useful:

**Never fail for a reason we could have found for free. Never spend the budget on something a

R$0 check would have killed. And never let a candidate die from a desk when it should have died on

the phone — or survive at a desk when the phone would have ended it.**

That is achievable, and the last two days proved it: **two front-runners killed in 48 hours, for

nothing, before a single call.** That is not failure. That is the machine working. The failure mode we

must actually prevent is different and specific — spending eight weeks building the wrong thing,

which nearly happened twice.

## 1. Where we actually are

•  48 candidates killed. All from a desk. Zero contact with a real buyer, ever.

•  The last two — FECHA MÊS and ESCALA DA FESTA — were killed by the same four-part sequence,

and by that sequence in the same order.

•  The screening method is now genuinely good. Candidate generation is not. Twelve lenses under the

old screen produced zero; forty-two candidates under the reversed screen produced eight viable, and

the two best died on segment facts that could have been checked first.

**The honest diagnosis: we have been screening candidates when we should have been screening

segments.** Neither finalist died of a product flaw. Fecha Mês died because trade-marketing agencies

number 108–500, not 179.702. Escala died because buffets with a real roster problem number 2.000–8.000,

not 128.000. Both were segment failures wearing candidate clothes.

## 2. What we own now — the assets, which are real and underused

| Asset | State |
| --- | --- |
| The full Receita Federal CNPJ base, processed | 13.033.275 active non-MEI companies; per-CNAE counts; phone and email fill rates per segment |
| The MEI-dilution test | IBGE keeps two registers; CEMPRE excludes MEI. Class 56.20-1: 500.092 MEIs vs 50.187 companies |
| The occupation-name test | Anexo XI of Res. CGSN 140/2018. If the MEI occupation reads *"…independente"*, the code is a workforce code and the count is a mirage |
| Measured phone reachability | MEI 0% · non-MEI 63,3% · EPP-and-larger 97,5%. Email is dead — the field returns the accountant's address |
| The measured price band | R$150–700 nominal, but capped hard where a whole ERP sells at R$99–299 |
| ~20 laws, each bought with a corpse | Law 0 (clearing party), Law A, Law C, the chat-window test, the precondition trap, the vise, Gate 0, the counterparty-motivation rule, the CNAE-mirage law, the liability-evidence law |
| The prefilled-claim engine | Find their public activity, build a page about them, open with *"posso te mandar a página já preenchida?"* |
| The AI/deterministic boundary | AI reads and drafts; code decides and calculates money |
| Her one asymmetry | She will telephone Brazilian businesses in Portuguese, all day. Nobody else in this search can |

## 3. The order in which candidates die — and therefore the order to test

Every kill in the last week followed the same sequence. This is the single most valuable pattern in

the record, and the plan is built on it.

| # | Test | What killed | Cost | Time |
| --- | --- | --- | --- | --- |
| 1 | POOL — how many *real operating firms*, not CNPJs? | Fecha Mês, Escala | R$0 | 1 hour |
| 2 | PAIN — can we find a *first-person* account in Portuguese of someone losing money to this? | Escala | R$0 | 2 hours |
| 3 | SHIPPED — does someone already sell it verbatim? Searched free-shaped and in vendor vocabulary | Fecha Mês, Escala | R$0 | 3 hours |
| 4 | PRICE FLOOR — what is the cheapest thing covering *part* of the job? | Escala (R$49,90 vs R$297) | R$0 | 1 hour |
| 5 | LIABILITY — does the artefact become evidence *against* the buyer? | Escala (TST: escala = poder diretivo) | R$0 | 1 hour |
| 6 | CHAT WINDOW — does ChatGPT do it in twenty minutes? | DeckProof | R$0 | 2 hours |
| 7 | CLEARING PARTY — who earns margin on the flow and will fund it to zero? | 7+ candidates | R$0 | 1 hour |
| 8 | HUMAN SUBSTITUTE — does a R$2.500 secretária absorb it? | 3 candidates | R$0 | 1 hour |

**Total: about twelve hours, R$0, and it would have killed both finalists before either got a

business plan.** Nothing proceeds past this gauntlet without passing all eight.

## 4. The plan

### PHASE 0 — Build the Segment Register · 5 days · R$0 · *This has never been done and every kill needed it*

Take the top 60 Brazilian CNAEs by non-MEI company count and put each through a fixed audit:

1. IBGE CEMPRE count (excludes MEI) — the real firm count, not the CNPJ count

2. Size distribution — firms with 10+ and 20+ people occupied (CEMPRE agg. 9529, PAS)

3. The occupation-name test — grep Anexo XI for that CNAE. Does it read *"independente"*?

4. The counter-terminal test — does this buyer's customer pay across a card machine? If yes, an

acquirer funds vertical software to zero. Segment excluded at source.

5. Phone contactability from the Receita base, by porte

6. The ERP price floor — is there a Brazilian vertical ERP at R$99–299 covering this trade?

7. Association reality check — but read correctly: for *professional* trades a directory is the

universe; for *local retail-like* trades it is not

**Output: a permanent, ranked register of segments that genuinely hold 20.000+ real operating firms,

reachable by phone, with no counter terminal and no whole-ERP floor.** Reusable forever. Every future

candidate starts here instead of dying here.

Gate 0: if fewer than eight segments pass, the constraint set itself is the problem and we say so

before spending another week.

### PHASE 1 — Generate against verified segments only · 4 days

Multiple lenses, reversed screen (adoption, not existence), but pointed exclusively at

Phase 0 survivors. No candidate may be proposed against an unaudited segment. Every schema carries a

whatIEliminatedAndWhy field — a zero-candidate run must still return its value.

Target: 20–30 candidates.

### PHASE 2 — Run the eight-test gauntlet · 3 days · R$0

In the order in §3. Cheapest killer first. A candidate that fails any test stops immediately — no

appeal, no repositioning. *Do not reinterpret a failure as "we need better positioning."*

Gate 1: at least two candidates clear all eight. If none does, return to Phase 1 once. If a second

pass also returns nothing, the constraint set is binding and that becomes the conversation.

### PHASE 3 — Contact · 12 days · under R$500 · **this is the phase that has never happened**

**This is the forcing function and it is non-negotiable: she is on the phone by day 25, with whatever

survived, even if it is imperfect.**

•  Build the list from the Receita base, filtered to non-MEI with a phone, in São Paulo first

•  200–250 dials, not 120 — a 5-in-120 threshold expects 2,4 closes at a true 2% and would kill a

working business on noise

•  Open with the prefilled-claim shape: an artefact about *them*, then *"posso te mandar?"*

•  Log the disqualifying question on every single call. Fifty owners answer for free the thing no

amount of research could settle

•  Pass bar, adopted verbatim from the best external memo we received:

*"Interest, deposits, positive feedback and 'we would use this again' do not count."*

Money committed, on the call, or it did not happen.

Gate 2: ≥2 unrelated prepayments. Below that, the candidate stops and Phase 1 restarts — but with

something no previous round has ever had: **real buyer language, real objections, and a measured

conversion rate.**

### PHASE 4 — Build only after money · 2–3 weeks

Smallest sellable version. AI reads and drafts; code decides and calculates money. No credential

custody, no per-transaction founder labour, no Meta dependency in the core promise. No-code stack with

Brazilian rails: Clicksign for contracts, Asaas for Pix and payouts, Supabase with row-level

security.

## 5. Timeline and budget

| Phase | Days | Cumulative | Cost |
| --- | --- | --- | --- |
| 0 — Segment Register | 5 | 5 | R$0 |
| 1 — Generation | 4 | 9 | R$0 |
| 2 — Gauntlet | 3 | 12 | R$0 |
| 3 — Contact | 12 | 24 | < R$500 |
| 4 — Build (only if paid) | 15–21 | ~45 | < R$500 |

She is talking to real buyers inside four weeks, and has spent under R$500 to get there.

## 6. What changes about how I work

Four commitments, each earned by a specific failure of mine in this record:

1. No number reaches her without its source and its unit checked. I produced *"R$11.750 per client

per month"* by dividing a global 2024 revenue figure by a *"+900 brands worldwide"* marketing claim

from a different page. I gave a segment count for one subclass that exceeded IBGE's count for the

whole class. Numerator and denominator must share a source, a date and a unit.

2. Segment before candidate. Always. Both finalists died on facts a one-hour audit would have

surfaced.

3. Every hunt schema carries `whatIEliminatedAndWhy`. Twelve lenses once returned zero and their

elimination work survived only in transcripts.

4. I flag my own uncertainty before the user has to find it. Three of my four stated concerns about

Escala were wrong. That is worse than saying nothing, because it aims the search at phantoms.

## 7. The decisions that are hers, not mine

I will not spend another week guessing at these:

1. Is R$30.000/month in 12 months still the target? Half of what has been killed would survive at

R$10.000/month, or at R$30.000 in three years. This single number has done more filtering than any

law in the file.

2. Does the audience/network exclusion still hold? It has been named as one of only three

load-bearing constraints since candidate 11 and has never moved. An anonymous topic page is

already permitted and has never been used.

3. How much per-transaction work is genuinely unacceptable? "No founder labour" killed several

candidates that would work at two hours a week.

4. Which buyer would she genuinely enjoy for two years? She rejected a fully validated candidate on

this, correctly. It is a real constraint and it is anti-correlated with Law 0 — the buyers she likes

mostly take cards at a counter, and acquirers fund their software to zero.

## 8. The one-sentence version

**Stop screening candidates and start screening segments; put her on the phone inside four weeks with

whatever survives eight free tests; and never again spend a week on a business that a one-hour audit

of IBGE would have ended.**

## 9. Standing watch item — autonomous computer-use agents (added 12 Aug 2026)

xAI announced Grok Bot (x.ai/news/introducing-grok-bot). Fetched and read, so the note is

accurate rather than a placeholder.

What it claims: an agent with its own cloud computer that *"sign[s] into the tools you already

use and work[s] across apps"*, runs 24/7 without the user present, *"finish[es] jobs end to end, and

only come[s] back when something needs your approval"*, learns preferences by observation, and

coordinates with other bots.

Status: beta, gated to SuperGrok Heavy, Cursor Ultra and Cursor Teams Premium; enterprise

waitlist. No public API or standardised agent interface mentioned. Not dependable as infrastructure

yet — which matches the founder's own read.

### The distinction that decides how it can be used

**It works across apps WITHOUT APIs by signing in as the user. That is simultaneously the capability

we needed and the thing we proved she cannot sell.**

•  As a PRODUCT mechanism: still closed. The whole government-action category died because the

authenticated write needs custody of the customer's e-CNPJ certificate or gov.br login, and a

faceless unknown seller asking a stranger for that inverts the trust gradient. An agent that signs

in on the customer's behalf does not fix that — it *is* that. Same wall, better robot.

Also unchanged: the gov.br Termo de Uso bans robots and access *"através de serviços de

hospedagem"*, which is what a cloud agent is.

•  As LEVERAGE ON HER OWN OPERATIONS: genuinely valuable, and the right place to point it. The

candidates that died on *per-transaction founder labour* (Aval, REAVER, the MCP service, arguably

Bancada) died because a human had to touch every transaction. An agent operating her own accounts,

her own back office, her own list-building and her own follow-up compresses exactly that cost — and

every credential involved is hers.

### When it leaves beta, research these four things specifically

1. Reliability on repetitive commercial work — not demos. Error rate on a hundred identical runs.

2. Whether it can be pointed at her own back office — list building from the Receita base, CRM

hygiene, follow-up sequencing, invoice and payout admin — without her touching each item.

3. Cost per completed job at volume, against the R$150–700/month price band. A tool that costs more

per customer than the subscription is not leverage.

4. Whether any product design becomes viable that was previously blocked ONLY by "no API" — and

whether it can be built so the *customer* runs the agent under their own credentials rather than her

holding them. That single architectural question decides whether the closed category reopens.

Do not re-open any killed candidate on the strength of this until item 4 is answered. "Better

automation" was never the binding constraint; trust and terms of use were.